## Sheet1
| PROJECT MANAGEMENT | VOLUNTEER SCHEDULE | FUNDRAISING | Cylinder1 | Cylinder2 | Cylinder3 | Cylinder4 | Cylinder5 | Cylinder6 | Cylinder7 | Cylinder8 | Cylinder9 | Cylinder10 | Cylinder11 | Cylinder12 | Cylinder13
2020-01-22 | *Proposal due!
2020-01-29 | Place orders for solar light, hardware, and material to use for half scale model. |  | Submit FIREFLY art grant proposal of bringing 5 cylinders to Vermont Regional burn.
2020-02-05 | Have half-scale model of one cylinder built. | Coordinate with committed fabrication site (Bluebird Graphic Solutions in Woburn) for cutting/building day.
2020-02-12 | Stress-test and 1/2 scale example installation. Have batteries installed, and powering some test lighting and sound effects. Searching for components most likely to fail. | Bring scale model to Blake Courtney's personal shop, work day.
2020-02-19 | Have necessary edits and adjustments made to the CAD / CNC production files. | Consult with CAD knowledgable volunteers (such as Hani), sharpen design.
2020-02-26 | Improve upon 1/2 scale model further, with replacement parts from design edits. | Coordinate and recut at Bluebird Shop, work at Blake's shop, if necessary.
2020-03-04 | *Proposal is accepted. Notify contributing artists, fabricators, and previously committed team. Place order for materials, and send CAD / CNC production files to Bluebird fabrication shop. Schedule a day for cuts and pickup. Rent storage space and fabrication space in Artisan's Asylum. | Purchase Artisan's asylum membership. Rent storage space, make early vehicle rental reservations. Make public call on Boston Burner Community, Blunderwood Portable, Windchest, or other Honoraria team email lists for volunteers. Schedule first volunteer production day for following week.
2020-03-11 | Cylinder1 begins production. | First volunteer production day. Artisan's asylum.
2020-03-15 | Art Installation Questionaire due
2020-03-16 | "Kickoff Meeting". Recieve, Review, and Sign Contract from BMOrg. Due March 31st. |  | Launch Patreon/Crowdfunding site for Revolutionary Labyrinth
2020-03-18 | Troubleshoot Cylinder1. If any adjustments are needed at full scale, fix them this week. If none, begin assembly line of pieces manufacturing for Cylinder2, Cylinder3. | Volunteer Production Day. Blake's shop. | Plan Fundraiser event in Boston area, book locations
2020-03-25 | Deliver Cylinder1 to Artist1 | Call up all artists this week. Email them templates and ask for a written description of their intended installation. |  | Installation begins
2020-03-31 | Signed Contract for BMOrg due on this day.
2020-04-01 | Deliver Cylinder2 to Artist2 | Volunteer Production day. Artisan's Asylum. |  |  | Installation begins
2020-04-08 | Deliver Cylinder3 to Artist3. |  |  | PM Check in call/visit |  | Installation begins
2020-04-15 | Deliver Cylinder4 to Artist4 | Volunteer Production day. Artisan's Asylum. |  |  | Check in Call/Visit |  | Installation begins
2020-04-22 | Deliver Cylinder5 to Artist5 |  |  | PM Check in call, Do they need more time? |  | Check in Call/Visit |  | Installation begins
2020-04-29 | Deliver Cylinder6 to Artist6. Consult with Artist 1 and pickup cylinder 1 to bring to storage, stage for truck-load readiness. |  |  | Pickup 1 | Check in call |  | Check in Call/Visit |  | Installation begins
2020-05-06 | Deliver Cylinder7 to Artist7. Pick up 2 for storage. |  |  |  | Pickup 2 | Check in call |  | Check in Call/Visit |  | Installation begins
2020-05-13 | Deliver Cylinder8 to Artist8. Pick up 3 for storage. |  | Fundraiser Event! |  |  | Pickup 3 | Check in call |  | Check in Call/Visit |  | Installation begins
2020-05-20 | Deliver Cylinder9 to Artist9. Pick up 4 for storage. | [5 empty] | Pickup 4 | Check in call |  | Check in Call/Visit |  | Installation begins
2020-05-27 | Deliver Cylinder10 to Artist10. Pick up 5 for storage. | [6 empty] | Pickup 5 | Check in call |  | Check in Call/Visit |  | Installation begins
2020-06-01 | Art Support Services (ASS) Resource Request due | [10 empty] | Check in Call/Visit
2020-06-03 | Deliver Cylinder11 to Artist11. Pick up 6 for storage. | [7 empty] | Pickup 6 | Check in call |  |  | Check in Call/Visit | Installation begins
2020-06-10 | Deliver Cylinder12 to Artist12. Pick up 7 for storage. | Volunteer Production day. Artisan's Asylum. | [7 empty] | Pickup 7 | Check in call |  |  |  | Installation begins
2020-06-17 | Deliver Cylinder13 to Artist13. Pick up 8 for storage. | Volunteer Production day. Artisan's Asylum. | Fundraiser Event 3 for showing off how far we've come and covering other important unmet expenses | [7 empty] | Pickup 8 | Check in call |  |  |  | Installation begins
2020-06-24 | Pick up 9 for storage, as well as other Cylinder#s that may have needed extra time. | Volunteer Production day. Artisan's Asylum. Cylinders should be complete at this point. | [9 empty] | Pickup 9
2020-07-01 | Crew members finalized, names for tickets and early arrivals submitted | Build Crew team meeting
2020-07-02 | No fabrication this week. Bring 5 completed Cylinders to Firefly (Vermont burning man regional). Test installation, install, power sytem, and cylinder-to-cylinder interaction on small grid scale. | [11 empty] | possibly no fabrication | possibly no fabrication | possibly no fabrication | possibly no fabrication
2020-07-08 | Return Cylinders 1-5, and Pick up 10, to storage space. should anything need troubleshooting, consult artists and make arrangements for alteration. | Build Crew and Volunteer production day in Storage Space with completed cylinders for adding LEDs to exterior | [10 empty] | Pickup 10
2020-07-15 | Pick up 11 for playa-ready storage. Have a cleaning day to get any matter from Firefly terrain off of the 5 cylinders. | Troubleshooting and testing LEDs and power with Carl and Blake | [11 empty] | Pickup 11
2020-07-22 | Pick up 12 for playa-ready storage. | [13 empty] | Pickup 12
2020-07-29 | Pick up 13th and final cylinder. Move all cylinders, disassembled into quadrants and labeled ALCs, to storage space before truck load. Run down checklist of components per cylinder, print multiple copies of assembly instructions for each installation and put one in each ALC. Label by color and name, ziptie associated ALCs together, as well as build crew camp supplies, generator and tools, and other materials needed on playa. WEEK LONG PROJECT | Large volunteer pull for pre-truck load! | [13 empty] | Final pickup
2020-08-01 | TRUCK LOAD. Transportation from Boston to BRC begins. | Huge volunteer pull for TRUCK LOAD!
2020-08-05 | Crew meeting. Prepping crew for playa, last minute organizational tasks. | Crew meeting is followed by volunteer appreciation party!
2020-08-12
2020-08-19 | Crew flies to Reno.
2020-08-26 | Build week and installation.
2020-08-30 | Build finished by sunrise. Burning Man Festival
2020-09-02
2020-09-07 | Strike Art Project and LNT begins. Disassemble and repack installation components into labeled boxes for return to boston. Load shipping container back at the Boston Hive neighborhood.
2020-09-09 | Crew regroup in Reno. Container with project + village and camp gear ships back to Boston.
2020-09-16 | Truck Unload in Boston, cleaning and storing labyrinth.
2020-09-23
2020-09-30 | Documentation and Final Report | Thank you notes for volunteers are made and mailed locally. | Thank you notes and fundraiser backer rewards are shipped out.
2020-10-15 | Final report and high-resolution images due